Local-First Work Intelligence System

Work Breakdown Structure and Delivery Plan

WBS  |  Version 1.0

21 September 2026

| Primary owner | Project Manager / Scrum Master |
| --- | --- |
| Target audience | Entire Delivery Team |
| Core question | In what order should the complete project be delivered, what depends on what, and what proves each work package complete? |
| Project status | Architecture defined; implementation and benchmark execution pending |

# Document Control

| Version | Date | Status | Purpose |
| --- | --- | --- | --- |
| 1.0 | 21 September 2026 | Baseline | Defines the approved project-level baseline for design and delivery. |

This document is intended to evolve under version control. Requirement IDs and architectural decision IDs should remain stable once referenced by downstream documents.

# Contents

| 1. Planning Basis | Assumptions, sequencing method and effort notation. |
| --- | --- |
| 2. Master Delivery Roadmap | Phase 0-5 sequence and major gates. |
| 3. Phase 0 — Foundation | Core evidence, storage, policy, runtime and telemetry. |
| 4. Phase 1 — Document Intelligence | End-to-end document ingestion and grounded Q&A. |
| 5. Phase 2 — Code + Git | Structural code and repository history intelligence. |
| 6. Phase 3 — Connectors | Read-only work-system integrations. |
| 7. Phase 4 — Semantic/Temporal Memory | Derived graph and temporal reasoning. |
| 8. Phase 5 — Enterprise | Multi-user, centralized operations and hardening. |
| 9. Cross-cutting Workstreams | Security, QA, benchmarks, docs, packaging and licenses. |
| 10. Critical Path and Dependencies | What cannot start/finish before other work. |
| 11. Release Gates | Objective exit criteria by milestone. |
| 12. Backlog After V1 Product | Optional future extensions beyond committed scope. |

# 1. Planning Basis

This WBS is a sequencing baseline for the entire product, not a contractual calendar. Week ranges assume a small core team (approximately 2-3 engineers with part-time product/QA/security support). A solo implementation should expect materially longer elapsed time; a larger team can parallelize work where dependencies permit.

Schedule principle — Do not begin expensive later-phase integration before the evidence lifecycle, policy boundary, trust contract and benchmark harness are stable. Those are load-bearing foundations.

| Notation | Meaning |
| --- | --- |
| S | Small work package; typically days. |
| M | Medium; roughly 1-2 engineer-weeks. |
| L | Large; multiple weeks or multiple disciplines. |
| Gate | Objective acceptance checkpoint; downstream phase does not depend on unverified assumptions. |

# 2. Master Delivery Roadmap

| Relative window | Milestone | Primary outcome | Dependency |
| --- | --- | --- | --- |
| Weeks 1-5 | M0 Foundation | Persistent evidence/control plane, policy, resources, telemetry, model abstraction and desktop skeleton. | None |
| Weeks 4-11 | M1 Document Intelligence | Document ingestion → hybrid retrieval → grounded answer with citations; packaging/resource/vector benchmarks. | M0 core schemas/policy |
| Weeks 10-17 | M2 Code + Git | Structural code search and historical repository investigation. | M1 retrieval/evidence/tool contracts |
| Weeks 16-24 | M3 Connector Framework | Connector SDK + priority read-only work systems. | M0 lifecycle + M1 retrieval |
| Weeks 23-30 | M4 Semantic/Temporal Memory | Derived entities/relations and timeline queries with provenance. | M1-M3 evidence breadth |
| Weeks 29-38 | M5 Enterprise Readiness | Multi-user authz, centralized deployment, ops, hardening and migration path. | Stable preceding data/tool contracts |

Parallelism is intentional: later phases may begin design/spikes before prior phase release, but production dependency contracts must be frozen first.

# 3. Phase 0 — Foundation

| WBS | Work package | Deliverable | Size | Depends on |
| --- | --- | --- | --- | --- |
| 0.1 | Project bootstrap | Repo, CI, Python/Tauri skeleton, formatting/lint/test harness | S | — |
| 0.2 | Domain schema | Workspace, AuthorizedSource, SourceItem, EvidenceVersion, EvidenceUnit, QueryContext | M | 0.1 |
| 0.3 | SQLite persistence | SQLAlchemy models, migrations, WAL/config, repository interfaces | M | 0.2 |
| 0.4 | Evidence content store | Content-addressed encrypted storage abstraction, manifests, integrity checks | M | 0.2 |
| 0.5 | Source registry | Authorize/list/revoke sources; local directory baseline | M | 0.2-0.3 |
| 0.6 | Policy Manager | Workspace/source/sensitivity/read-only policies | M | 0.2-0.5 |
| 0.7 | Resource Controller | Memory/CPU snapshot, budgets, priorities, admission decisions | M | 0.1 |
| 0.8 | Inference Gateway | Provider protocol + Ollama adapter + model aliases/timeouts | M | 0.1 |
| 0.9 | Audit/OpenTelemetry | Query/job IDs, traces, safe audit events | M | 0.1-0.3 |
| 0.10 | Agent control skeleton | Separate worker + tool allow-list + parent-owned tool execution | L | 0.6-0.8 |
| 0.11 | Security baseline tests | Unknown tool denial, no shell/write/network, prompt injection fixture | M | 0.10 |
| G0 | Foundation gate | Source can be authorized/versioned; evidence persists; agent cannot bypass policy; system restarts safely. | Gate | 0.1-0.11 |

# 4. Phase 1 — Document Intelligence

| WBS | Work package | Deliverable | Size | Depends on |
| --- | --- | --- | --- | --- |
| 1.1 | File discovery/watch | Recursive scan, exclusions, watchfiles events, reconciliation sweep | M | G0 |
| 1.2 | Fingerprint/versioning | Streaming hash, unchanged detection, immutable version creation | M | 1.1 |
| 1.3 | Docling adapter | PDF/DOCX/PPTX/XLSX/TXT/MD/HTML/image parse path | L | 1.2 |
| 1.4 | OCR/large-doc controls | Scanned detection, batch/page limits, worker recycling | M | 1.3,0.7 |
| 1.5 | Normalization | EvidenceUnit location/structure mapping, content persistence | M | 1.3 |
| 1.6 | FTS5 index | Schema, BM25/exact search, deletion/version filters | M | 1.5 |
| 1.7 | Vector adapters | LanceDB adapter + Qdrant Edge benchmark adapter | L | 1.5,0.8 |
| 1.8 | Embedding pipeline | Qwen embedding provider, cache, batching, model-versioned collections | M | 1.7 |
| 1.9 | Retrieval Manager | Parallel FTS/vector, filters, RRF, candidate budgets | L | 1.6-1.8 |
| 1.10 | Reranker | Qwen reranker adapter, bounded rerank, bypass heuristics | M | 1.9 |
| 1.11 | Evidence Resolver | Exact body reads, bundle builder, provenance/citation objects | M | 1.9 |
| 1.12 | Fast query path | Classification, retrieval, one generate call, trust finalize | M | 1.11,0.8 |
| 1.13 | Investigative path | DeepAgents bounded tool loop over knowledge tools | L | 1.11,0.10 |
| 1.14 | Trust Manager | Sufficiency, citation validation, conflict handling, abstention | L | 1.12-1.13 |
| 1.15 | Desktop UX | Source setup, ingestion status, chat, citations/evidence viewer, errors | L | 1.12 |
| 1.16 | Vector benchmark | 50k/100k/500k synthetic/realistic chunks; RAM/latency/disk/update/delete | M | 1.7-1.9 |
| 1.17 | Embedding/rerank benchmark | 0.6B vs 4B quality/latency/resource evaluation on curated corpus | M | 1.8-1.10 |
| 1.18 | Resource benchmark | Idle/query/ingestion RSS/CPU; concurrent query vs indexing | M | 1.4,1.12-1.13 |
| 1.19 | Packaging spike | Tauri + Python sidecar; PyInstaller/Nuitka comparison; clean-machine smoke | L | 1.3,1.7,1.15 |
| 1.20 | License/SBOM gate | Dependency/model licenses, SBOM, disallowed-license check | M | 1.19 |
| G1 | Document Intelligence gate | Representative document corpus answers with exact citations, bounded RAM and no paid/cloud dependency. | Gate | 1.1-1.20 |

# 5. Phase 2 — Code + Git

| WBS | Work package | Deliverable | Size | Depends on |
| --- | --- | --- | --- | --- |
| 2.1 | Language support matrix | Choose priority languages and Tree-sitter grammars | S | G1 |
| 2.2 | Tree-sitter parser | Definitions/symbols/scopes/imports/references normalized to code evidence | L | 2.1 |
| 2.3 | Structural index | Schema/query APIs for symbols, refs, files/modules | L | 2.2 |
| 2.4 | Git adapter | Read-only commits/trees/blobs/diffs/blame/renames | L | G1 |
| 2.5 | History index | Commit/file/version relations and searchable change metadata | L | 2.4 |
| 2.6 | Code retrieval tools | find_symbol/find_references/search_code/read_code_evidence | M | 2.3 |
| 2.7 | History tools | search_history/compare_revisions/read_historical_blob | M | 2.5 |
| 2.8 | Hybrid fusion extension | Fuse lexical/vector/structural/history candidates | M | 2.3,2.5,G1 |
| 2.9 | Impact analysis | Deterministic reference graph + clearly labeled inferred impact workflow | L | 2.6-2.8 |
| 2.10 | Repo benchmark | Known implementation/reference/change/history questions across fixture repos | M | 2.8-2.9 |
| G2 | Code/Git gate | Where/what-changed/history/reference questions meet benchmark and citation traceability. | Gate | 2.1-2.10 |

# 6. Phase 3 — Connectors

| WBS | Work package | Deliverable | Size | Depends on |
| --- | --- | --- | --- | --- |
| 3.1 | Connector SDK | Common adapter, cursor, deletion, rate-limit, credential contracts | L | G1 |
| 3.2 | Secret abstraction | OS keyring integration hardened; enterprise secret provider interface | M | 0.6,3.1 |
| 3.3 | Connector priority research | Select first 2-3 systems by user value/API feasibility | S | 3.1 |
| 3.4 | Connector A | Implement discovery/sync/content/provenance/revocation | L | 3.1-3.3 |
| 3.5 | Connector B | Implement same contract | L | 3.1-3.3 |
| 3.6 | Connector C | Optional third priority connector | L | 3.1-3.3 |
| 3.7 | Sync scheduler | Cursor checkpoints, retries, rate limiting, incremental refresh | M | 3.4-3.6 |
| 3.8 | Cross-source retrieval | Source-type filters, authority classes, mixed evidence UX | M | G1,3.4+ |
| 3.9 | Connector conformance suite | Replay/deletion/token-expiry/permission-loss/outage tests | M | 3.4-3.7 |
| G3 | Connector gate | Priority systems sync read-only with correct provenance/revocation and no secret leakage. | Gate | 3.1-3.9 |

# 7. Phase 4 — Semantic/Temporal Memory

| WBS | Work package | Deliverable | Size | Depends on |
| --- | --- | --- | --- | --- |
| 4.1 | Use-case benchmark | Define questions graph must improve vs baseline retrieval/agent | M | G1-G3 |
| 4.2 | Entity ontology | Project/Decision/Requirement/Component/Issue/Person/etc. minimal schema | M | 4.1 |
| 4.3 | Relation schema | Deterministic/inferred types, provenance, confidence, valid-time | M | 4.2 |
| 4.4 | Extractor pipeline | Entity/relation extraction with evidence links and versioned model/config | L | 4.2-4.3 |
| 4.5 | Graph backend spike | Benchmark free OSS/local options only after query needs are concrete | M | 4.3 |
| 4.6 | Graph retrieval | Entity/time/path queries feeding Evidence Resolver/agent | L | 4.4-4.5 |
| 4.7 | Retraction/rebuild | Revocation propagation and rebuild from evidence | M | 4.4-4.6 |
| 4.8 | Temporal UX | Timelines, supersession/conflict visualization and citation links | L | 4.6 |
| 4.9 | A/B benchmark | Prove graph materially improves target questions without faithfulness loss | M | 4.1,4.6 |
| G4 | Semantic memory gate | Graph demonstrates measurable value and remains fully provenance-backed/rebuildable. | Gate | 4.1-4.9 |

# 8. Phase 5 — Enterprise

| WBS | Work package | Deliverable | Size | Depends on |
| --- | --- | --- | --- | --- |
| 5.1 | Enterprise topology | Central API/workers/storage/index deployment design | L | G2-G4 |
| 5.2 | Identity integration | User/session/SSO adapter boundary | L | 5.1 |
| 5.3 | Fine-grained auth | OpenFGA or equivalent OSS adapter; workspace/source/tool relations | L | 5.2 |
| 5.4 | Enterprise secrets | OpenBao or equivalent provider integration | M | 5.1 |
| 5.5 | Shared vector/index service | Evaluate migration to Qdrant Server/service topology if scale needs it | M | 5.1 |
| 5.6 | Admin console | Workspace/source/policy/health/audit controls | L | 5.2-5.4 |
| 5.7 | Backup/restore/DR | Authoritative DB/content backup, index rebuild, key management procedures | L | 5.1 |
| 5.8 | Scale/load testing | Concurrent users, large corpora, worker scaling, model throughput | L | 5.1-5.5 |
| 5.9 | Security hardening | Threat model, pen test, tenant isolation, credential/audit review | L | 5.2-5.8 |
| 5.10 | Upgrade/migration | Desktop-to-enterprise data migration and rolling schema/index upgrades | L | 5.1-5.8 |
| G5 | Enterprise gate | Multi-user security, operations, scale, backup/restore and licensing all pass release criteria. | Gate | 5.1-5.10 |

# 9. Cross-cutting Workstreams

| Workstream | Runs throughout | Outputs |
| --- | --- | --- |
| QA/benchmarking | All phases | Golden corpora, regression tests, retrieval/answer metrics, performance baselines. |
| Security | Foundation onward | Threat model, tool-policy tests, prompt-injection fixtures, secret/authz reviews. |
| Observability | Foundation onward | Trace schemas, dashboards/diagnostics, latency/error/resource metrics. |
| Licensing/SBOM | Every dependency/model change | SBOM, license inventory, policy gate and replacement plan for incompatible components. |
| Documentation | Every gate | ADRs, admin/user docs, migration/runbooks and benchmark reports. |
| UX research | Document phase onward | Citation usability, trust messaging, source setup, historical/graph visualization. |
| Data migration | Whenever schema/index/model changes | Migration scripts, compatibility tests, rollback/rebuild plan. |

# 10. Critical Path and Dependencies

Evidence identity/versioning → authoritative storage → policy filtering are foundational and must precede meaningful retrieval/agent work.

Document parsing/normalization must stabilize enough to produce benchmarkable EvidenceUnits before selecting a vector backend/model tier.

Retrieval/Evidence Resolver must exist before the agent loop; otherwise the agent will absorb responsibilities that belong in deterministic services.

Trust/citation validation must be complete before calling document intelligence “done”.

Code/Git and connectors reuse the same evidence lifecycle; do not create parallel lifecycle systems.

Semantic/temporal memory starts only after enough heterogeneous evidence exists to benchmark whether it adds value.

Enterprise tenancy/authz starts only after source/evidence/tool ownership contracts are stable enough to enforce centrally.

# 11. Release Gates

| Gate | Must be true before proceeding |
| --- | --- |
| G0 Foundation | Policy deny-by-default; persistent versioned evidence; resource/audit/inference abstractions; safe agent tool boundary. |
| G1 Documents | Supported formats ingest; retrieval benchmark passes; citations resolve; abstention works; resource/package/license benchmarks pass. |
| G2 Code/Git | Structural/history facts trace to exact revisions; implementation/change/history queries pass. |
| G3 Connectors | Read-only scopes, sync/replay/revocation, secret isolation and mixed-source retrieval pass. |
| G4 Semantic | Graph adds measurable query value; inferred relations remain labeled/provenance-backed/retractable. |
| G5 Enterprise | Tenant/workspace auth, centralized ops, backup/restore, scale, security and upgrade tests pass. |

# 12. Backlog After V1 Product

Optional write-capable workflow automation as a separately permissioned product mode, never silently added to read-only intelligence.

Voice/mobile clients using the same query/evidence APIs.

Federated cross-device indexes with privacy-preserving sync.

Policy-aware proactive alerts/briefings using scheduled jobs.

Advanced dependency graphs and build/runtime telemetry integration.

Organization-wide analytics over anonymized/authorized work patterns, subject to explicit governance.